## Gantt Chart with Critical Path
GANTT CHART WITH CRITICAL PATH TEMPLATE
| PROJECT NAME | Product Release |  |  | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE
| PROJECT MANAGER | Alex B. |  |  | 2025-09-02 | 2025-10-10 | 35% | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION in days | STATUS | COMMENTS | STATUS
| SPRINT 1 |  | Alex B. |  | 2025-09-03 | 2025-09-13 | 10 | Complete |  | Complete
| Feature 1 |  | Frank C. |  | 2025-09-03 | 2025-09-07 | 4 | Complete |  | Overdue
| Feature 2 |  | Jacob S. |  | 2025-09-07 | 2025-09-12 | 5 | Complete |  | In Progress
| Feature 3 |  | Jacob S. |  | 2025-09-09 | 2025-09-13 | 4 | Complete |  | Not Started
| SPRINT 2 |  | Jacob S. |  | 2025-09-16 | 2025-09-24 | 8 | In Progress |  | On Hold
| Feature 4 |  | Alex B. |  | 2025-09-16 | 2025-09-17 | 1 | In Progress
| Feature 5 |  | Frank C. |  | 2025-09-17 | 2025-09-21 | 4 | Overdue
| Feature 6 |  | Shari W. |  | 2025-09-22 | 2025-09-24 | 2 | On Hold
| SPRINT 3 |  | Shari W. |  | 2025-09-25 | 2025-10-05 | 10 | Not Started
| Feature 7 |  | Alex B. |  | 2025-09-25 | 2025-09-29 | 4 | Not Started
| Feature 8 |  | Kennedy K. |  | 2025-09-27 | 2025-10-02 | 5 | Not Started
| Feature 9 |  | Jacob S. |  | 2025-10-02 | 2025-10-05 | 3 | Not Started
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Gantt Chart
GANTT CHART WITH CRITICAL PATH TEMPLATE
| PROJECT NAME |  |  |  | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE
| PROJECT MANAGER | [6 empty] | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION in days | STATUS | COMMENTS | STATUS
| SPRINT 1 | [5 empty] | 0 |  |  | Complete
| Feature 1 | [5 empty] | 0 |  |  | Overdue
| Feature 2 | [5 empty] | 0 |  |  | In Progress
| Feature 3 | [5 empty] | 0 |  |  | Not Started
| SPRINT 2 | [5 empty] | 0 |  |  | On Hold
| Feature 4 | [5 empty] | 0
| Feature 5 | [5 empty] | 0
| Feature 6 | [5 empty] | 0
| SPRINT 3 | [5 empty] | 0
| Feature 7 | [5 empty] | 0
| Feature 8 | [5 empty] | 0
| Feature 9 | [5 empty] | 0
Cut, paste, and adjust arrows to illustrate critical paths.
Double click Horizontal (Value) Axis to format Bound Minimum and Maximum settings under Axis Options.

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.