## EXAMPLE Software Contingency
SOFTWARE CONTINGENCY PLAN TEMPLATE
PROJECT NAME |  | NAME
PROJECT MANAGER |  | NAME |  |  | DATE | MM/DD/YY
|  | Enter Risk Category titles on the Dropdown Key tab to populate the Risk Register Dropdown Menu. |  |  |  |  | DO NOT ALTER SCORE CELLS Outcomes populate automatically.
REF ID | DATE RAISED | RISK CLASS | RISK DESCIPTION | IMPACT DESCIPTION | PROBABILITY 1 – 5 | IMPACT 1 – 16 | PRIORITY LEVEL Prob x Impact | CONTINGENCY PLAN STRATEGY | TRIGGER POINTS | END PLAN TRIGGER | ACTION | OWNER | NOTES
10001 | MM/DD/YY | Planning | If there are changes in plans that require additional or different resources, then there will be delays. | If there are changes in plans that require additional or different resources, then there will be delays. | 1 | 8 | 8 | A designated team member will continually monitor any proposed changes in plans and ensure communication between teams about proposed changes. | What triggers the contingency scenario? | What triggers the end of the contingency plan? |  | Joe Smith; liaison
10002 | MM/DD/YY | Contracts | If contractual issues among contractors, subcontractors, or vendors arise, then there will be delays or cost overruns. | If contractual issues among contractors, subcontractors, or vendors arise, then there will be delays or cost overruns. | 2 | 4 | 8 | The manager will continually monitor contracts, alert the team when there are issues, and ensure that the team addresses and resolves contract issues before they cause delays. |  |  |  | Sue Johnson, contracts manager
10003 | MM/DD/YY | Permits / Regulations | If obtaining appropriate construction permits takes longer than planned, then there will be delays. | If obtaining appropriate construction permits takes longer than planned, then there will be delays. | 2 | 8 | 16 | The manager, or another designated team member, will monitor the project schedule and deadlines and ensure that all permits can accommodate the project's schedule. |  |  |  | Dale Swenson, manager
10004 | MM/DD/YY |  |  |  | 1 | 8 | 8
[5 empty] | 1 | 1 | 1
[5 empty] | 1 | 2 | 2
[5 empty] | 1 | 4 | 4
[5 empty] | 1 | 8 | 8
[5 empty] | 1 | 16 | 16
[5 empty] | 2 | 16 | 32
[5 empty] | 3 | 16 | 48
[5 empty] | 4 | 16 | 64
[5 empty] | 5 | 16 | 80
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Software Contingency Plan
SOFTWARE CONTINGENCY PLAN TEMPLATE
PROJECT NAME |  | NAME
PROJECT MANAGER |  | NAME |  |  | DATE | MM/DD/YY
|  | Enter Risk Category titles on the Dropdown Key tab to populate the Risk Register Dropdown Menu. |  |  |  |  | DO NOT ALTER SCORE CELLS Outcomes populate automatically.
REF ID | DATE RAISED | RISK CLASS | RISK DESCIPTION | IMPACT DESCIPTION | PROBABILITY 1 – 5 | IMPACT 1 – 16 | PRIORITY LEVEL Prob x Impact | CONTINGENCY PLAN STRATEGY | TRIGGER POINTS | END PLAN TRIGGER | ACTION | OWNER | NOTES
[5 empty] | 1 | 1 | 1
[5 empty] | 1 | 1 | 1
[5 empty] | 1 | 1 | 1
[5 empty] | 1 | 8 | 8
[5 empty] | 1 | 1 | 1
[5 empty] | 1 | 2 | 2
[5 empty] | 1 | 4 | 4
[5 empty] | 1 | 8 | 8
[5 empty] | 1 | 16 | 16
[5 empty] | 2 | 16 | 32
[5 empty] | 3 | 16 | 48
[5 empty] | 4 | 16 | 64
[5 empty] | 5 | 16 | 80
CLICK HERE TO CREATE IN SMARTSHEET

## Dropdown Keys – DO NOT DELETE –
PROJECT RISK REGISTER – MATRIX
PROBABILITY ¦ 1 – 5 | IMPACT ¦ 1 – 16 | PI SCORES ¦ 1 – 80 |  | 1 | 2 | 3 | 4 | 5
1 - RARE | 1 - INSIGNIFICANT | 1 – 2 • NEGLIGIBLE | 1 | 1 | 2 | 3 | 4 | 5
2 - UNLIKELY | 2 - MINOR | 3 – 8 • LOW | 2 | 2 | 4 | 6 | 8 | 10
3 - POSSIBLE | 4 - MODERATE | 10 – 16 • MEDIUM | 4 | 4 | 8 | 12 | 16 | 20
4 - LIKELY | 8 - MAJOR | 20 – 32 • HIGH | 8 | 8 | 16 | 24 | 32 | 40
5 - ALMOST CERTAIN | 16 - SEVERE | 40 – 80 • EXTREME | 16 | 16 | 32 | 48 | 64 | 80
PROBABILITY KEY | IMPACT KEY
1 | 1
2 | 2
3 | 4
4 | 8
5 | 16
Enter Risk Category titles below to populate the Risk Register Dropdown Menu.
RISK CATEGORY
Category One
Category Two
Category Three
Category Four
Category Five
Category Six
Category Seven
Category Eight
Category Nine
Category Ten
PROBABILITY
IMPACT

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.