## Video Project Timeline
VIDEO PROJECT TIMELINE
| PROJECT NAME | [5 empty] | START DATE
| PROJECT MANAGER | [5 empty] | END DATE
AT RISK | TASK | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
| Choose a story | Complete |  | 2024-01-02 | 2024-01-08 | 6 |  | Not Started
| Determine length | Complete |  | 2024-01-04 | 2024-01-11 | 7 |  | In Progress
| Write script | Complete |  | 2024-01-07 | 2024-01-11 | 4 |  | Complete
| Create shooting script | Complete |  | 2024-01-10 | 2024-01-15 | 5 |  | On Hold
| Create script breakdown | Complete |  | 2024-01-13 | 2024-01-20 | 7
| Create a storyboard | Complete |  | 2024-01-16 | 2024-01-29 | 13
| Determine the budget | In Progress |  | 2024-01-19 | 2024-02-01 | 13
| Scout and select locations | In Progress |  | 2024-01-22 | 2024-02-09 | 18
| Get location permits and permissions | In Progress |  | 2024-01-25 | 2024-02-05 | 11
| Determine equipment needs | On Hold |  | 2024-01-28 | 2024-02-06 | 9
| Inventory existing equipment | In Progress |  | 2024-01-31 | 2024-02-02 | 2
| Task 12 | In Progress |  | 2024-02-04 | 2024-02-12 | 8
| Task 13 | Not Started |  | 2024-02-06 | 2024-02-14 | 8
| Task 14 | Not Started |  | 2024-02-09 | 2024-02-17 | 8
| Task 15 | Not Started |  | 2024-02-18 | 2024-02-20 | 2
| Task 16 | Not Started |  | 2024-02-15 | 2024-02-23 | 8
| Task 17 | Not Started |  | 2024-02-18 | 2024-02-26 | 8
| Task 18 | Not Started |  | 2024-02-21 | 2024-02-29 | 8
| Task 19 | Not Started |  | 2024-02-24 | 2024-03-03 | 8
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Video Project Timeline
VIDEO PROJECT TIMELINE
| PROJECT NAME | [5 empty] | START DATE
| PROJECT MANAGER | [5 empty] | END DATE
AT RISK | TASK | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
| Choose a story |  |  |  |  | 0 |  | Not Started
| Determine length |  |  |  |  | 0 |  | In Progress
| Write script |  |  |  |  | 0 |  | Complete
| Create shooting script |  |  |  |  | 0 |  | On Hold
| Create script breakdown |  |  |  |  | 0
| Create a storyboard |  |  |  |  | 0
| Determine the budget |  |  |  |  | 0
| Scout and select locations |  |  |  |  | 0
| Get location permits and permissions |  |  |  |  | 0
| Determine equipment needs |  |  |  |  | 0
| Inventory existing equipment |  |  |  |  | 0
| Task 12 |  |  |  |  | 0
| Task 13 |  |  |  |  | 0
| Task 14 |  |  |  |  | 0
| Task 15 |  |  |  |  | 0
| Task 16 |  |  |  |  | 0
| Task 17 |  |  |  |  | 0
| Task 18 |  |  |  |  | 0
| Task 19 |  |  |  |  | 0
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.